### Worksheet Template 1: Understanding the Project’s GEDSI Context

Project Title: Example Project

Narrative/summary:

The primary GEDSI stakeholders for our project are women who have started families or are elderly, although they are not always visible in the community, we anticipate that they will be the ones who will be implementing much of the findings of our project and we aim to engage them through focus group discussions throughout the project. There are several marginalized communities (groups of urban poor, many of whom are migrants) that will need to be engaged to make sure that the project fully considers their needs and perspectives. People with disabilities are more difficult to engage through our project tasks, and we will be connecting with the local and national Disabled People’s Organisations, and working to include the needs of disabled people through focus group discussions with women and with socially marginalized groups.

Our project team is also bringing on additional GEDSI support and will engage a young volunteer from the urban migrant community to ensure team diversity, build capacity at the local level, and ensure GEDSI is being fully incorporated into the project work.

| Stakeholder / group | Interest, Influence | GEDSI issues | GEDSI risks & mitigation | Project engagement, communications |
| --- | --- | --- | --- | --- |
| Women – aged 30 + | High interest, low to medium influence | These women will implement many of the findings but are not always present in decision making, or at community consultation meetings due to busy schedules, care responsibilities, and community roles. | The risk is that we will not be able to fully engage these women in each step of the project. We have identified some women leaders in our project area and will work with them consistently to set up focus group discussions with other women. | Through identified women leaders, we will establish informal focus group discussions in small groups (5-8 per FGD) to ensure sufficient engagement (at least 50 women total). We will also use these focus groups to identify persons with disabilities that need to be consulted or engaged to support our project aims. |
| Migrant groups (urban) |  |  |  |  |
| Other socially marginalized groups in project area |  |  |  |  |
| Disability Organisations – local |  |  |  |  |
| Disability Organisations – national |  |  |  |  |
| Persons with disabilities |  |  |  |  |

### Worksheet Template 2: Applying a GEDSI lens to the Project

Project Title: Example Project

| Project element / timeframe | GEDSI consideration | Implementation approach | Comments |
| --- | --- | --- | --- |
| Design: Theory of Change | How will GEDSI stakeholders be engaged | GEDSI stakeholders incorporated into ToC | Need to connect with Disabled Peoples Organisations |
| Design: Risk Assessment | Collecting GEDSI disaggregated data through project interventions to ensure GEDSI-related people and issues are considered | GEDSI-disaggregated data to be collected | Data to feed into MEL |
| Design: Project team | Team does not fully reflect diversity of communities where project will be implemented | Recruit young volunteer/intern from urban social migrant community | Need to determine role description and management support, depending on who is recruited |
| Implementation: Community-based Workshops | Schedule workshops in conjunction with other community meetings to ensure greater participation, collect GEDSI-disaggregated data. | Co-lead workshops with community leaders to ensure relevance and uptake of ideas. | Even though a few women are present, only men speak. Consider other ways to gather representative participation and engagement. |
| Implementation: Women Focus Group Discussions |  |  |  |
| Implementation: Research design and methodology |  |  |  |
| MEL |  |  |  |
| Project reporting |  |  |  |
| Academic manuscript |  |  |  |